## ISP Internship Gantt
Phase | Date Range | Main Activities | Start Date | End Date
Phase 1 | 2026-03-29 to 2026-04-11 | Introduction to ISP workflow and network infrastructure; Understanding ISP service structure and technical environment; Basics of routers, DNS, and network communication; IP configuration and addressing fundamentals; Assisted in device checking and connectivity verification; Handling basic user complaints and service requests; First-level troubleshooting techniques; Observation of connectivity issues and network behavior; Performing basic network tests (ping, connectivity checks); Introduction to escalation process in ISP support | 2026-03-29 | 2026-04-11
Phase 2 | 2026-04-12 to 2026-04-25 | Advanced IP configuration and subnet understanding; DNS troubleshooting and resolution techniques; Router configuration basics and management; LAN/WAN connectivity analysis; Network device testing and fault identification; Handling user-side connectivity complaints; Use of diagnostic tools (ping, tracert, ipconfig); Identifying common network errors and causes | 2026-04-12 | 2026-04-25
Phase 3 | 2026-04-26 to 2026-05-09 | Advanced network troubleshooting techniques; Analysis of network outages and downtime issues; Wi-Fi connectivity troubleshooting; IP conflict detection and resolution; Router and modem issue handling; Network performance observation; Root cause analysis of connectivity failures; Practical ISP support case handling | 2026-04-26 | 2026-05-09
Phase 4 | 2026-05-10 to 2026-05-23 | ISP customer service and technical support workflow; Ticket handling and issue documentation; Escalation procedures for complex network issues; Monitoring network stability and performance; Troubleshooting frequent user complaints; Basic network security awareness in ISP environment; Coordination with senior technicians | 2026-05-10 | 2026-05-23
Phase 5 | 2026-05-24 to 2026-06-06 | Advanced router and network configuration exposure; DHCP and DNS issue resolution in real cases; Network fault isolation techniques; Handling large-scale connectivity issues; ISP infrastructure monitoring basics; Advanced troubleshooting case practice; Service optimization techniques | 2026-05-24 | 2026-06-06
Phase 6 | 2026-06-07 to 2026-06-20 | Documentation of troubleshooting cases; Real-time ISP support case analysis; Preparation of technical reports; Review of network issues handled during internship; Data organization and record keeping; Drafting internship report | 2026-06-07 | 2026-06-20
Phase 7 | 2026-06-21 to 2026-06-29 | Final internship report completion; Presentation slide preparation; Review of overall learning and experience; Supervisor feedback collection; Final submission and evaluation; Internship closure activities | 2026-06-21 | 2026-06-29